## Sheet 1
Table 1
Type | Task | Description | Status | Assign To | ETA | Remarks
Infra | Create EC2 instance |  |  | Suraj
Infra | Install MY SQL DB |  |  | Suraj
Infra | Install Apache Tomact |  |  | Suraj
Infra | Install Elasticsearch |  |  | Suraj
DB | Auto ID for Property ID, Profile ID |  |  | Suraj
DB | Datatype to store profile picture |  |  | Suraj
DB | App Ref data - City |  |  | Suraj | 2020-10-18 | Excel and DB Entry
DB | App Ref data - Area |  |  | Suraj | 2020-10-18 | Excel and DB Entry
DB | App Ref data - Localities |  |  | Suraj | 2020-10-18 | Excel and DB Entry
DB | App Ref data - State |  |  | Suraj | 2020-10-18 | Excel and DB Entry
DB | App Ref data - Landmark |  |  | Suraj | 2020-10-18 | Excel and DB Entry
DB | App Ref data - Pin Code |  |  | Suraj | 2020-10-18 | Excel and DB Entry
DB | app ref data for newly added field |  |  | Suraj | 2020-10-18 | Excel and DB Entry
DB | AUDIT of POST_PROPERTY (INSERT, UPDATE, DELETE) |  |  | Suraj
DB | AUDIT of USER_PROFILE (INSERT, UPDATE, DELETE) |  |  | Suraj
DB | AUDIT of APP_REF_DATA (INSERT, UPDATE, DELETE) |  |  | Suraj
UI | Implement Property Filter |  |  | Suraj
Infra | Jenkins - Build and Deployment |  |  | Suraj
MW | Change project name rsa tech to paroont |  | In Progress | Rahul
MW | Elastic Search Integration - App |  |  | Rahul
DB | Data sync from MySQL to Elasticsearch |  |  | Suraj
| Search Property |  |  | Rahul | 2020-10-18
| Test Data Insert - Post Property |  |  | Suraj/Alok | 2020-10-18
| Post Property - UI |  |  | Rahul | 2020-10-30