## Sheet 1
Table 1
Type | Task | Description | Status | Assign To | ETA | Remarks
Infra | Create EC2 instance |  |  | Suraj
Infra | Install MY SQL DB |  |  | Suraj
Infra | Install Apache Tomact |  |  | Suraj
Infra | Install Elasticsearch |  |  | Suraj
DB | Auto ID for Property ID, Profile ID |  |  | Suraj
DB | Datatype to store profile picture |  |  | Suraj
DB | App Ref data - City |  |  | Suraj | 2020-10-18 | Excel and DB Entry
DB | App Ref data - Area |  |  | Suraj | 2020-10-18 | Excel and DB Entry
DB | App Ref data - Localities |  |  | Suraj | 2020-10-18 | Excel and DB Entry
DB | App Ref data - State |  |  | Suraj | 2020-10-18 | Excel and DB Entry
DB | App Ref data - Landmark |  |  | Suraj | 2020-10-18 | Excel and DB Entry
DB | App Ref data - Pin Code |  |  | Suraj | 2020-10-18 | Excel and DB Entry
DB | app ref data for newly added field |  |  | Suraj | 2020-10-18 | Excel and DB Entry
DB | AUDIT of POST_PROPERTY (INSERT, UPDATE, DELETE) |  |  | Suraj
DB | AUDIT of USER_PROFILE (INSERT, UPDATE, DELETE) |  |  | Suraj
DB | AUDIT of APP_REF_DATA (INSERT, UPDATE, DELETE) |  |  | Suraj
UI | Implement Property Filter |  |  | Suraj
Infra | Jenkins - Build and Deployment |  |  | Suraj
MW | Change project name rsa tech to paroont |  | In Progress | Rahul
MW | Elastic Search Integration - App |  |  | Rahul
DB | Data sync from MySQL to Elasticsearch |  |  | Suraj
| Search Property |  |  | Rahul | 2020-10-18
| Test Data Insert - Post Property |  |  | Suraj/Alok | 2020-10-18
| Post Property - insert |  |  | Rahul | 2020-10-30
UI | View property details
UI | Search Property -agent details
UI | Post Property - search
UI | Post Property - search filter
UI | Post property _share on whatsapp
whats app integration
SMS otp validation
UI | user profile creation
UI | User profile update
Search suggestion -post property and property
build and packaging
release on play store
testing via link (url)
Elastic Search Integration with db
Manual testing
services notification
user support
UI font and theme
Icon collection
paroont.com integration